## Sheet1
Objective | Outcome | Timeline
Clarify HCH Strategic Planning Structure and Process | Initiative Work Plan Approved | 2017-10-01
Conduct Needs, Gaps and Strengths Assessment | Establish Understanding of HCH’s Current Structure and Operations | 11/1/2017 - 11/13/17
| Complete Comparative Analysis of similar HCH Programs throughout the state | 11/13/17 - 12/4/2017
| Develop Structure and Content for Stakeholder Input | 12/4/2017 -12/18/17
| Conduct Stakeholder Input Surveys, Interviews and Events | 12/18/18 - 3/30/18
| Analysis and Report of Stakeholder Data | 3/30/18 - 4/6/18
Compile Common Themes and Priorities Present in Needs, Gaps and Strengths Assessment
Evaluate and Align HCH Vision, Mission and Scope | Achieve Agency Alignment on Program Mission and Scope | 4/6/18 - 4/27/18
Program Vision Statement Updated
Program Mission Statement Updated
Develop Strategic Goals and Priorities | Analysis of Stakeholder Themes and Priorities | 4/27/18 - 5/18/18
Identify HCH Areas of Expertise
Develop and Prioritize Strategic Goals
Finalize HCH Strategic Plan | Draft Strategic Plan | 5/18/18 - 6/15/18
Submit Strategic Plan for Approval and Finalize
Develop Implementation Action Plan | Identify Core Areas of Work | 6/15/18 - 6/29/18
Assessment Program Resources and Capacity
Draft Implementation Action Plan
Create structures and processes to improve effectiveness and efficiency of HCH | Develop Quality Improvement and Program Dashboards | 6/15/18 - 8/10/18
Continued Assessment of Meeting Schedule aligned with Mission/Priorities
Finalize Quality Improvement Structure and Membership
Staffing and Personnel | Evaluate Current Staffing Model | 6/15/18 - 8/10/18
Evaluate Growth Opportunity Internally and Externally
Hone/Develop Internal Org Chart and Reporting Structure
Establish HCH Role in the Homeless Services System | Solidify HCH Areas of Expertise | 8/2018- 8/2021
Develop Strategy and Marketing Materials to Communicate HCH Functions, Role, Available Resources and Scope
Strengthen and build collaborative relationships among agencies serving the homeless
Implementation of HCH Strategic Plan and Establish Mechanisms for Sustainability | Cohesive, Coordinated and Consistent Agency Functions Honed and Operational